## Sheet1
LAST UPDATE: 05/176/2024
STRATEGY 1: Build resilient communities and organizations through activities that position the region to attract new populations, enhance econimic diversity, adapt ot the local and national impacts of climate change, and empower them to thrive ina complex and uncertain future.
ACTION | METRIC | TARGET | START DATE | END DATE (if applicable) | ACTUAL | PROGRESS
Work directly with communities to educate on the nature of resiliency, and how communities are at risk and can increase resiliency in their operations. | The number of projects funded in support of new services, such as climate change adaptation work | 1-2 |  |  | 4 | -Convened 3 Resiliency meetings in Richland County with diverse stakeholders -Incorporated resiliency and climate change issues in the Hazard Mitigation Plans for Grant, Iowa, and Lafayette Counties -A FEMA BRIC grant to fund work in all 5 counties is preliminarily approved. Formal approval is expected in the summer or fall, 2024
Help develop local housing working groups. Include best practices used throughout the region and return on investment analyses to generate local support for community investment in housing. | Number of groups convened | 1-2 |  |  | 2 | -Shullsburg's Comprehensive Planning Implementation Committee is focusing on housing with consultation from SWRWPC on land use size, TIF funding, and use of local funds -Lone Rock's Economic Development Committee is adopting a new TIF Plan written by SWWRPC which will be used to invest in new housing
Continue to engage in long-range planning, including comprehensive and strategic planning tied to community climate resiliency and economic diversification. | The number of comprehensive, strategic, and outdoor recreation plans completed | 1-2 |  |  | 5 | -Green County Strategic Plan proposed for 2024 -Green County Broadband Plan to complete in August 2023 -Richland County Comprehensive Plan -Mineral Point Comprehensive Plan and Strategic Plan
Work with school districts to develop opportunities for increased collaboration and shared services, and to help them grow enrollment. | The number of contracts or districts engaged | 1-2 |  |  |  | -No action yet, but planning and strategy conversations have been held with Cassville, Boscobel, Highland, Dodgeville, Shullsburg, Belmont, Monticello, Monroe, Juda, school districts and CESA 3 -School enrollment data trends, including trends on open and natural enrollment, are tracked and mainteained. Working on historic trends for operating levy success
Grow our conservation and ecological planning work to include watershed plans and GIS modeling. | New contracts or services offered | 1-2 |  |  | 2 | -Created an urban forestry work plan generating contract revenue -Partnered with the Driftless Area Land Conservancy on GIS analysis of critical habitats and development pressures
Work on community marketing and branding projects to support local placemaking and workforce attraction efforts. | The number of projects implemented | 2-3 |  |  | 3 | -Community "marketing audits" completed and implementation strategy is being discussed. -Cassville branding will kick-off in June, 2023 -Mineral Point marketing contract pending award in June, 2023
Engage communities to modernize their ordinances to ensure flexibility and enable unique community amenities and development models. | The number of ordinances updated | 1 |  |  |  | Discussion and assistance with Lone Rock, Lancaster, Avoca, and Rewey. No ordinances updated by SWWRPC to date
Develop renewable energy plans to grow the amount of renewable energy generated on municipal and publicly-owned buildings. | The number of plans created | 1
Develop county and local climate change adaptation strategies that identify at-risk assets, opportunities for economic growth through workforce and business attraction. | The number of projects funded in support of new services, such as climate change adaptation work | 1-2 |  |  |  | Scoping discussion is underway to build a regional project on the foundation of the Richland Resiliency group and completed County Hazard Mitigation Plans. Projects in Richland County are being locally-driven through volunteer efforts
STRATEGY 2: Grow the economy through our unique role in the region, and by adding value to our partners' work by advising on project enhancements that lead to increased sustainability and greater return on community investments.
ACTION | METRIC | TARGET | START DATE | END DATE (if applicable) | ACTUAL | PROGRESS
Continue to aggressively pursue EDA and other economic development capacity building grants to develop land and financing for economic growth. | # of grants per year | -1 infrastructure grant every other year -1 planning grant every other year |  |  |  | -Discussion is underway with Fennimore and Shullsburg on new industrial park grants -Grant submitted to study to combine Potosi and Tennyson's water system
Update the regional Comprehensive Economic Development Strategy to align the work of partners such as Prosperity Southwest Wisconsin, EDA, Wisconsin Economic Development Corporation, and local economic development efforts to maximize the use of our minimal resources. Include strategies and tactics to increase climate and economic resiliency for the region. | -CEDS updated to meet this requirement | 2024 Update |  |  |  | -CEDS process is underway with the update due in August, 2024
Support projects that attract childcare facilities, new housing development, and other necessary community amenities required to attract workforce. | The number of projects supported or led. | 1-2 projects |  |  | 4 | SWWRPC is leadingt TIF planning proceses for Lone Rock, Shullsburg, New Glarus, and Monticello. We completed a TIF plan for housing in Mineral Point and will be assisting with new housing development.
Help our communities become welcoming to new and diverse populations that are required to maintain community events, tax base, workforce, and school enrollment. | Communities engaged | 2-3 |  |  | 1 | Secured an Economic Recovery Coordinator (Francis Henn) to support work in Lancaster and build networks throughout the region
STRATEGY 3: Create new partnerships that build resiliency thorugh reduced expenses and improved efficiencies among local government and non-profit partners.
ACTION | METRIC | TARGET | START DATE | END DATE (if applicable) | ACTUAL | PROGRESS
Serve as project managers and implementation monitors for SWWRPC-led plans. | The number of projects in SWWRPC-conducted plans that are implemented by local communities | 3-4 |  |  | 5 | -Creation of a Lone Rock on a TIF district -New housing moving forward in Darlington and Shullsburg -TIF plan develoment in Lone Rock, Monticello, and Richland CEnter to fund housing and other Comp Planning projects. -Municipal administrative consulting in Richland Center to assist with operational efficiencies which will enable economic development operations. -Leading trail and path planning efforts in Monticello through Green County Leaders
Continue to develop tools such as the Asset Map and Constructability Map to assist in on-boarding new partners, rapidly respond to development opportunities, reduce time required to prepare grants, and maintain regional institutional knowledge. | Maintenance or creation of new tools | 2-4 |  |  | 3 | -The constructability map was updated to show WEDC-eligible areas, historic EDA investment areas, new census data informing grant eligibility, and TIF boundaries and financial information -Creation of a new TID Planning Tool -Redevelopment of the existing Verified Sites tool
Facilitate the development of shared service agreements between organizations which result in reduction of administration and overhead costs while maintaining high-quality service-delivery. | [5 empty] | -No action yet. Creation of an internal list of potential partnership projects.
Serve as the regional administrative agent for projects that span counties or cities in order to reduce overhead and administrative burdens at the local level. | The number of contracts secured | 2-4 |  |  | 1 | -Facilitation of the BEAD Planning Grant on behalf of PSW which enabled each county to get an additional 10% revenue from the state
Increase relationships and collaborative projects with networks outside of the region, including statewide agencies or private sector firms, in order to increase statewide awareness and funding to the region. | The number of projects, partnerships, or initiatives created | 2-4 |  |  | 3 | -Partnering with WEDC to improve alignent between EDA and WEDC funding streams and programs. -Membership on a regional equitable housing coalition -Membership on multiple climate or resiliency steering committees or teams
STRATEGY 4: Maintain capability and capacity to execute on this strategy.
ACTION | METRIC | TARGET | START DATE | END DATE (if applicable) | ACTUAL | PROGRESS
Maintain competitive market-rate compensation and benefits packages, and evaluate compensation packages every two years at a minimum. | Annual turnover rate and reason for turnover | 0% turnover |  |  | 10% | -2023-2024 salary and benefit increases were more closely aligned with inflation -Salary suggests ability to hire high entry-level candidates when combined with mission and work flexibility. -Increase in vacation and holidays recommended for approval by the Executive Committee. Discussion on Paid Family leave was held.
Continue to conduct annual staff evaluations, semi-annual retention meetings, and exit interviews to maintain a positive organizational culture and ensure alignment of staff with our mission. | Annual turnover rate and reason for turnover | 0% turnover |  |  | 10% | -Evaluations complete for 2023. Staff appear happy. We continue to need to monitor wages and workload to avoid burnout. -Exit interview held with departing staff to gain input on the causes of departure
Continue to diversify operational revenue to enhance the investment of our partner counties, while also providing financial independence and operational resiliency. | -Grant revenue as a percentage of overall revenue to measure revenue diversification -The number of annual contracts awarded by value and overall count -Annual growth of on-going, sustainable revenue | Balance of revenue streams |  |  |  | -Developed an urban forestry consulting service -Engaged with our first community for GIS mapping of infrastructure -Secured 4 TIF planning contracts -Secured one contract for municipal financial and operational consulting -Grant and contract revenue grows at a faster rate than county contribution increases
Continue to improve upon existing strong SWWRPC marketing efforts through direct marketing to municipalities and the growth of our newsletters and annual report distribution through our partners. | -Annual report and 3 quarterly newsletters -Frequent Facebook posts | 4 publications per year Weekly posts |  |  | 4 | -Newsletters distributed quarterly except for when the Annual Report is distributed -Annual report developed
Increase new funding streams from state and federal agencies such as WEDC, USDA, and EPA. | -Grant revenue as a percentage of overall revenue to measure revenue diversification -The number of annual contracts awarded by value and overall count -Annual growth of on-going, sustainable revenue |  |  |  |  | -One WEDC Grant awarded for 2024 -PSC BEAD Planning Grant -FEMA BRIC Grant pending award -High potential for USDA grant for AI support in 2025
Continue to invest in staff professional development, including project management and leadership training, in order to ensure all staff are able to lead and manage team projects. | Annual investment in professional development and training |  |  |  |  | -Basic Economic Development: Jaclyn and Misty in 2023, Alyssa in 2024 -Certified Tree Management Institute: Cory 2023 -Ellen attended a Welcoming Communities training, and Resilient Communities Training -Troy attended a WEDC / EDA alignment strategy training, WEDC, and NADO -American Planning Association: Jaclyn to Wisconsin in 2023, Alyssa to National in 2024 -Jaclyn and Austin are attending Green County Leaders -Ellen is beginning a 2-year Certified Public Manager Course -Troy and Ellen - Argonne Institute National Resilience Conference 2024 -Austin to Wisconsin Land Information Council 2023 -Kate to International Economic Development Conference 2023 -Troy to National Assocation for Development Organizations Conference 2024
STRATEGY 5: Enhance the decision-making ability of local organizations through the provisoin of quality data, maps, scenario lanning, and strategic thinking.
ACTION | METRIC | TARGET | START DATE | END DATE (if applicable) | ACTUAL | PROGRESS
Remain the region’s premier data and GIS provider through continued analysis of new data trends and synthesis of relevant data sources. | # of annual data requests | 5-8 |  |  | 15 | Hiring a data science major from UWP, Jacob Nelson, has enhanced our productivity in data analysis and also brought in-house ability to generate population projections. We continue to find and analyze new data on new topics to aid communities in decision-making. -Approximately 15 request for data and maps in the past 12 months
Continue to provide local public engagement, board facilitation, and community surveys to help communities identify core issues and opportunities, and create informed, publicly-supported policies and projects. | # of annual presentations or engagements held | 5-8 |  |  | 2-3 | -Assisted county Emergency Management Directors with IPPW Survey -Presentation on demogrpahics and workforce for the Green County Board
Continue to provide data analyses to local communities and organizations to assist with strategy development and decision-making. | # of data packets provided to local partners | 5-8 |  |  | 6 | -Provided demographic, income, and health data to the Lafayette County Health Department for their CHNA -In discussion with Grant Regional Health to assist with the combined CHNAs for their hospital, Boscobel, and Prairie du Chien hospital -Prepared data for Lancaster, Town of Wyoming, Town of Clyde, and Hickory Grove
Maintain current databases from sources such as the US Census and the Wisconsin Departments of Revenue and Public Instruction, and maintain active use of EMSI’s modeling tool. | [5 empty] | -Work continues to build our database through projects such as the CEDS, Housing Studies, and local comprehensive plans -Database improvements and the support of our Research Analyist make maintenance on spreadsheets less necessary than was historically the case
Continue to engage GIS as a decision-making and asset management tool, growing the number of public web maps for use by partners and the public. | The number of GIS maps or platforms created | 5-8 |  |  | 8 | -Public and private on-line maps have been created for Dickeyville, Boscobel, Green County, Iowa County, Driftless Area Land Conservancy. -Belmont Solar Priority Map created -Constructability map provided to Richland Center -Demographic map of the region created